SilicaGuard

Occupational Lung Health Platform: Module 1: Silicosis

Screen · Track · Follow Through

MASTER REFERENCE DOCUMENT · Version 6.0 · Final Showcase Edition

| Field | Detail |
| --- | --- |
| Team Lead | Panashe M. Chandiwana — AI & Backend Engineer |
| Team Member 2 | Takudzwa — Mobile, Web & Design Engineer |
| Team Member 3 | Gabriel — Clinical Lead, Research & Pilot Lead |
| Assigned Mentor | Dr S. Bopoto · +263 773 565 182 · sbopoto@cimas.co.zw |
| SUBMISSION DEADLINE | Monday 24 August 2026 presentation AND 5-minute prototype video |
| Final Showcase | Friday 28 August 2026 — in person, Top 10 |
| Build window | 14–20 August. Feature freeze 20 August. 21–23 August is video and deck only. |
| Pilot location | Kwekwe District, Midlands Province |
| Supersedes | v5.0 and all earlier versions. Single source of truth. |

Structure. Part A maps section-for-section onto the organisers' mandated presentation template  build the deck straight from it. Part B is the strategic depth that backs Part A in Q&A. Part C is execution. Appendices carry the evidence base and the modelling backlog.

# Section 0 | What Changed in Version 6.0

The organisers' final instructions arrived and they change the plan in three material ways. Read this section before anything else.

CRITICAL: The deadline is Monday 24 August, not 28 August. The presentation and the 5-minute video must both be submitted by then. The 28th is the showcase; the 24th is when the work has to be finished. That removes four days from every previous plan.

| Change | What it means | Consequence |
| --- | --- | --- |
| Submission by 24 August | Deck and video both due. Organisers need time to review and test all material. | Feature freeze moves to 20 August. 21–23 August is video production and deck finalisation only. |
| Mandatory 5-minute recorded video | It is played during our presentation on the day. It is the primary demonstration, not a backup. | New major deliverable. Whole day allocated to shooting (21 Aug), whole day to editing (22 Aug). Section 6 is the plan. |
| Live prototype must still be ready | Judges may request a live demonstration or clarification. | The system must be running and stable on the 28th, not just on video. The USSD simulator and seeded demo data must survive a week. |
| Fixed presentation template | Eight prescribed sections, in order. | Part A of this document is written to that structure. Do not reorder it. |
| In-person presentation | Confirmed physical showcase. | Printed handouts, physical logistics, device charging, offline fallback all now certain rather than assumed. |

## 0.1 The one gap the template exposes

The template asks explicitly for “stakeholders/users engaged.” We have desk research, one verification call with Dr Gunda, and mentor feedback from Dr Bopoto. We have not spoken to a single artisanal miner, village health worker, or hospital clinician. Every other section we can answer strongly. This one we currently cannot.

Ten days is enough to fix this substantially. Section 4.2 is a seven-day engagement plan. Treat it as the highest-priority non-code task in this document — it is worth more marks than any feature we could still build.

# Section 1 | Scope Decisions, Locked

Already decided. Strip these from the codebase, from SILICAGUARD.md, from the deck, from the video script, and from every conversation.

| Removed | Why | Still needs cleaning in |
| --- | --- | --- |
| Formal / enterprise mining scope | Dr Bopoto's feedback. Formal mining companies already run pneumoconiosis programmes and their workers are covered by NSSA. Not the underserved problem. | Revenue model (rewritten, Section 14), employer tables, dashboard role names |
| Chest X-ray and imaging AI | We do not read radiographs and must never imply we do. Silicosis confirmation requires an X-ray read against ILO classification — hospital work. | Endpoint names, Swagger examples, README, old slides |
| WhatsApp channel | Requires a smartphone, paid data, Meta business verification, and cannot reach a user outside a 24-hour window. USSD and SMS reach every phone. | Schema remnants, docs |
| Voice / IVR education | Provider coverage for Zimbabwe unestablished; unbounded external risk. | Docs only |
| QR referral card | Reframed, not deleted — see 1.1. | Feature list — replace with 'referral code' |

## 1.1 The QR referral card — reframed

The idea was: a referred miner carries a QR code to the hospital; a clinician scans it, the full screening record opens, and the referral is automatically marked attended. That automatic attendance confirmation is genuinely valuable — it makes our headline KPI measurable without any extra admin.

But a QR needs hospital-side scanning we do not control, there is no printer at a mine site, and it is useless to a USSD self-screener — the very population we are proudest of reaching.

The decision

Build the referral code, not the QR card. Each referral generates a short human-readable code — SG-4K7Q — sent by SMS to the miner and included in the facility pre-alert. Hospital staff type it into one simple web page: the record opens and the referral closes as attended. Works on a feature phone, needs no app on the hospital side, needs no printer. A QR becomes a later convenience layer that auto-fills the same code, so nothing is wasted.

PART A

The Presentation — mapped to the organisers' template

The eight sections below are the organisers' prescribed structure, in their order. Build the deck directly from these. Everything in Part B exists to defend these claims under questioning, not to be presented.

# Section 2 | Team & Solution Introduction

| Required element | Our answer |
| --- | --- |
| Team name | Team SilicaGuard |
| Solution name | SilicaGuard |
| One-sentence description | SilicaGuard is a mobile and USSD lung-health screening system that finds silicosis early in Zimbabwe's artisanal miners and tracks every referral until the miner actually reaches a hospital. |

## The team, in one line each

- Panashe M. Chandiwana — Computer engineer. Built the backend, the four AI modules, the USSD and SMS layer, and the safety-override architecture.

- Takudzwa — Mobile, web and design engineer. Built the practitioner app, the dashboard and everything the user sees.

- Gabriel — Medical student and Clinical Lead. Owns clinical validity, every patient-facing string, the risk logic and the pilot research design.

Worth saying out loud in one sentence: an engineer and a clinician built this together, which is why the safety logic sits outside the AI model rather than inside a prompt.

OPEN / VERIFY: Confirm 'Team SilicaGuard' is the name you registered with. If you registered under a different team name, use that one — a mismatch on the organisers' programme looks careless.

# Section 3 | The Healthcare Problem

## 3.1 What problem are we solving?

Silicosis is an incurable lung disease caused by breathing fine silica dust from rock drilling and ore crushing. The dust lodges permanently, the lungs slowly harden, and no medicine reverses it. Finding it early and getting the man out of the dust is the entire treatment — which makes screening not one option among several, but the whole intervention.

Zimbabwe has no system doing that for the people most exposed. There is no register, no re-screening schedule, no referral tracking, and no live data. Not because the medicine is unknown, but because the delivery infrastructure has never existed.

## 3.2 Who is affected?

- Half a million artisanal and small-scale miners — Roughly 500,000 people, with about 2 million dependants and close to 6 million with a stake in the sector.

- Young men, mid-thirties — Mean age 35.5. This is a disease being contracted with decades of working life still ahead.

- The workforce producing most of Zimbabwe's gold — Small-scale miners delivered 34.9 of the record 46.7 tonnes in 2025 — about three quarters. The formal gold sector employs roughly 18,000 people; artisanal mining involves around 500,000. A ratio of about 28 to 1.

- People with no occupational health cover at all — Silicosis is compensable in Zimbabwe only for workers formally employed by organisations contributing to NSSA's scheme. Artisanal miners are informal. They get the disease and none of the protection.

## 3.3 Evidence that the problem exists, in Zimbabwe

| Finding | Figure | Source |
| --- | --- | --- |
| Silicosis prevalence, community study | 19% of 3,821 artisanal miners; TB 6.8%; HIV 18%; mean age 35.5 | Moyo et al., IJERPH 2022, 19:13822 |
| Silicosis in the screened cohort | 21% — 2,150 of 10,282 miners screened | Moyo et al., IJERPH 2024, 21:70 |
| TB burden versus the general population | 7,400 per 100,000 in miners versus 190 per 100,000 nationally — 39 times higher | IJERPH 2024, 21:70 |
| Compounding risk | Silicosis raises TB risk 3–4×; HIV 5–6×; both together more than 15× | IJERPH 2024, 21:70 |
| Follow-up failure | Only 73% of eligible miners were started on TB preventive therapy, attributed to high mobility and remote operation | IJERPH 2024, 21:70 |
| Local mortality signal | Clinicians at Kwekwe District Hospital report approximately one silicosis death per week | Newsletter reporting citing Dr Gunda, verified by direct telephone follow-up |

OPEN / VERIFY: The Kwekwe mortality figure is the weakest link in this table because it is not documentary. Either obtain something written from the hospital in the next ten days, or present it exactly as phrased above — attributed to clinicians, verified by us — rather than as a hard statistic.

## 3.4 The number that makes the problem land

Zimbabwe's most serious attempt at this was the Kunda Nqob'iTB project: USAID-funded, run by a specialist occupational health provider, operating in eight priority districts with two dedicated clinics and a mobile screening facility. Between October 2020 and September 2023 it screened 10,668 artisanal miners.

10,668 ÷ 3 years = ~3,556 miners per year

500,000+ ÷ 3,556 per year ≈ 141 years for a single screening round

At the best pace this country has ever achieved, screening the artisanal mining population once would take about one hundred and forty years. Silicosis is progressive and incurable. There is no version of this where the arithmetic works. This is the centrepiece slide, and every number in it is the programme's own.

## 3.5 And whatever gets built, disappears

| When | What happened |
| --- | --- |
| 2019–2024 | KNTB runs as a five-year USAID cooperative agreement; miner screening Oct 2020 – Sep 2023 |
| 2024 | Funding ends. Nothing digital replaces the paper system. |
| 2025 | Zimbabwe Health Interventions' US$53.2 million USAID grant, scheduled to September 2026, terminated abruptly in the aid funding freeze. |
| Feb 2026 | Zimbabwe formally terminates negotiations on the proposed health funding MoU with the United States. |
| Jul–Aug 2026 | MoHCC, the Global Fund and ZHI run a two-week mobile TB and silicosis outreach in Shurugwi. Same model, same province, ended 8 August. |

Why this is the argument, not a footnote

Donor-funded, campaign-shaped occupational health for this population has collapsed twice in two years. A judge assessing implementation is not asking whether the problem is real. They are asking whether our answer survives the next funding shock. That is precisely what SilicaGuard is designed around.

# Section 4 | Validation & Current Workflow

## 4.1 Research conducted

- Peer-reviewed literature — Primary sources are two IJERPH papers by Moyo and colleagues — the 2022 Triple Burden prevalence study and the 2024 KNTB project report — which together give us prevalence, programme design, throughput and documented failure points.

- Primary verification — The prevalence and mortality figures reached us first through a newsletter article citing Dr Gunda. We did not stop at the citation — we telephoned him directly to verify the numbers before building the risk model on them.

- Live programme monitoring — We tracked the MoHCC/Global Fund/ZHI Shurugwi outreach running 27 July to 8 August 2026 and used it to test our positioning against a programme operating in real time.

- Policy analysis — We traced the WHO/ILO/ICOH Basic Occupational Health Services model and confirmed, from Zimbabwe's own occupational health researchers, that the country has not implemented it — and that their published recommendation is to start in artisanal mining districts.

- Funding landscape — We documented the collapse of KNTB and the termination of ZHI's grant to understand why previous efforts ended, which directly shaped our sustainability model.

## 4.2 Stakeholders and users engaged — and the seven-day plan to strengthen it

Engaged to date: Dr Bopoto as assigned mentor, whose feedback produced a merged scope change; and Dr Gunda by telephone for data verification. Gabriel brings clinical training to every design decision as a team member rather than an external consultee.

CRITICAL: We have not yet spoken to an artisanal miner, a village health worker, or a hospital clinician. The template asks for this explicitly. Closing even part of this gap in the next seven days is worth more than any remaining feature.

### The plan — target eight to twelve structured conversations by 21 August

| Who | How to reach them | What to ask | Owner |
| --- | --- | --- | --- |
| 3–5 artisanal miners | Through a Kwekwe syndicate contact, or any ASM association. Phone is fine — no need to travel. | Have you ever been screened? When you were told to go to a clinic, did you go — and if not, why? Do you have a phone, and would you dial a code? What would make you trust this? | Gabriel + Panashe |
| 2–3 village health workers | Gabriel's clinical network; district health office | Walk me through what you do now. Would you use a phone app in the field? What would stop you? How many people could you realistically see in a day? | Gabriel |
| 1–2 Kwekwe District Hospital clinicians | Named clinical contact; outpatient or respiratory | How do miners present now? What happens to a referral? Would a pre-alert and a referral code help or add work? | Gabriel |
| Dr Bopoto — formal session | Already engaged; book a structured session | Review of the final pitch, the pilot design and the ask. Document what changes as a result. | Panashe |
| Dr Gunda — structured follow-up | Already spoken; go back properly | The Kwekwe mortality figure in writing; his view on the triage-not-diagnosis framing. | Gabriel |
| Baines OHS or UZT | Cold email is acceptable and a reply is itself evidence | We are building X to solve the follow-up problem your report describes. Would you look at it? | Panashe |

How to record it so it counts

Keep one table with five columns: date, name and role, what they told us, what changed in the product or the plan as a result, and whether we may quote them. That table is the validation slide. A judge cares far less about the number of conversations than about visible evidence that something changed because of them — which is exactly what we can already show for Dr Bopoto's feedback.

## 4.3 The current process, and where it hurts

This is how occupational health screening for artisanal miners actually works today, from the published programme report. Knowing it in this detail is what separates us from teams who have read a headline.

| Stage | What happens now | The pain point |
| --- | --- | --- |
| Demand creation | A two-day visit at least a week before the event: clinical staff, MoHCC focal persons, ASM association leadership and mobilisation officers announce the event, distribute posters, build rapport, assess road access. | It is an event cost repeated every time, and it ends when the team leaves. |
| Site selection | A pre-visit picks no more than four sites, on anticipated reach, accessibility and leadership permission. | Judgement rather than optimisation, and capped at four. |
| Screening — mobile | Screening set up at or near the mine with multiple workstations. Requires hired ablutions, a generator, furniture, equipment and consumables trucked to site. Quarterly, four days per event. | The equipment is what caps coverage. Four days a quarter, four sites. |
| Screening — clinic | Two occupational health clinics exist in the whole country, at Gweru and Gwanda provincial hospitals. Symptom tool plus chest radiograph plus clinical evaluation, all free. | Two clinics for 500,000 miners, and miners must travel to them. |
| Recording | Paper occupational health examination form; entries in daily attendance, TB and TPT registers; manual import into Excel for weekly analysis. | Retrospective, manual, and invisible to anyone making decisions in real time. |
| Referral and follow-up | Verbal instruction; the miner is handed to the MoHCC clinic nearest the screening site. | Only 73% of eligible miners started preventive therapy. High mobility makes follow-up fail. Nobody knows who did not arrive. |
| Re-screening | No defined interval and no recall mechanism. | Screening is an event, not surveillance. No memory of the miner between visits. |

One more documented failure worth naming: fewer miners were screened for silicosis than for TB, because of power outages and X-ray maintenance. The entire silicosis pathway is gated on radiology being available.

## 4.4 Existing alternatives and their limitations

| Alternative | What it does well | Where it falls short |
| --- | --- | --- |
| Donor-funded mobile outreach (KNTB, ZHI/Global Fund) | Real diagnostics on site — radiography, sputum, HIV testing, spirometry. Trusted institutional presence. Genuine community access. | Episodic: quarterly, four days, four sites. Caps out around 3,556 miners a year. Ends when the grant ends — twice in two years. No tracking between events. |
| Occupational health clinics | High diagnostic yield; free to miners; integrated into public hospitals. | Only two exist nationally. Miners must travel. Reaches the already-sick rather than the still-working. |
| General primary health care | Present in every district — 185 health facilities across the five Midlands project districts alone. | Almost none have occupational health capability. Zimbabwe has not implemented the basic occupational health services model, and there are very few staff trained in it. |
| Doing nothing / self-presentation | No cost. | Silicosis is silent for a decade. Nobody self-presents early. By the time a man seeks care, the damage is irreversible. |

The honest positioning line

None of these alternatives is wrong. They are all correct and all capped. What none of them has is a layer that runs between the events — remembering the miner, watching him deteriorate, and chasing the referral until it closes. That is the gap, and it is the only thing we claim.

# Section 5 | Proposed Solution

## 5.1 How it works

A village health worker walks onto a mine site with a phone, a power bank and a small team. She runs a fifteen-minute group education session using Teach Mode — six illustrated cards with a script underneath, so a worker with two days of training delivers the same session a nurse would. Then she screens each miner individually: ten questions, about ten minutes, in Shona or English.

The system does four things with that screening. It classifies the miner into one of four risk levels, with hard clinical safety rules running in code after the AI responds, so a RED can never be downgraded. It compares this screening against his last one and escalates the level if anything has worsened, even when today's score alone would not have flagged him. It tells him the single most important thing he could change, drawn from his own weakest answer. And where a referral is needed, it creates a tracked referral: the right facility, a deadline, an SMS pre-alert to the clinic, a referral code to the miner, reminders on day three and day seven, and escalation on day fourteen if nobody has confirmed he arrived.

Miners who miss the outreach day dial a USSD code from any phone — no smartphone, no data. Same ten questions, same scoring, same record, same referral. The result comes back by SMS as a numbered level rather than a colour, because colour does not survive plain text.

## 5.2 Who uses it

| User | What they do with it | Interface |
| --- | --- | --- |
| Village health workers and clinic nurses | Screen miners at the mine site; run group education; generate and track referrals; work their follow-up queue; plan outreach visits | Practitioner mobile app — works offline |
| Artisanal miners | Get screened; self-screen any time; receive results, advice and reminders | In person, then USSD and SMS on any handset |
| District hospitals | Receive pre-alerted referrals; open a miner's record from his referral code; confirm attendance | Web dashboard plus a single code-entry page |
| MoHCC and district health | See live tier distribution, site breakdown and a plain-language weekly narrative for their catchment | Web dashboard |
| NSSA, Cimas, Ministry of Mines | Population-level occupational disease burden for the informal mining workforce | Web dashboard, role-filtered |

## 5.3 Where it fits in the healthcare workflow

Upstream of the clinic, never inside it. We are a triage and tracking layer that sits between the mine site and the hospital door.

Mine site → VHW screening / USSD self-screen → risk level → referral → HOSPITAL (diagnosis) → outcome recorded → re-screen scheduled

Everything in capitals stays exactly where it is today. We do not diagnose, we do not treat, and we do not read radiographs. We decide who needs a clinician, make sure the clinician knows they are coming, and make sure they actually arrive. The formulation to use on stage: we do not replace the X-ray — we decide who gets on the X-ray list first, and we make sure they turn up.

## 5.4 Key value delivered

| Value | Concretely |
| --- | --- |
| Coverage that is not capped by equipment | A health worker with a phone is not a four-day event. Modelled at roughly 19,200 screenings a year with ten VHWs, against the incumbent's 3,556. |
| Memory of the miner | Every re-screen is compared to the last. Deterioration is caught before an absolute score would flag it. Nothing existing does this. |
| Referrals that close | Deadline, pre-alert, reminders, escalation, and a code the hospital enters to confirm attendance. Against a documented 73% baseline for follow-through. |
| Reach without a smartphone | USSD self-screening reaches miners in remote shafts and those absent on outreach day — the ones every campaign misses. |
| Live population data | Tier distribution, site breakdown and a weekly narrative computed continuously, replacing paper registers and retrospective Excel. |
| Cost that survives a funding gap | The marginal cost of one additional screening is roughly one SMS. No mobile clinic fleet to sustain. |

# Section 6 | Prototype Demonstration & the 5-Minute Video

This is the single most important new deliverable. It is played during our presentation, which makes it the primary demonstration rather than a backup. The instruction is explicit: demonstrate the core functionality rather than every feature.

## 6.1 What to show, and what to leave out

| Show | Leave out |
| --- | --- |
| One returning miner screened end to end, with deterioration detected | The registration flow, settings, login screens |
| The four-level result with the personalised advice line, in Shona and English | The full question bank — show three or four questions, not ten |
| A referral created, with facility, deadline and code | Outreach Planner detail, Teach Mode card-by-card |
| A real SMS arriving on a physical handset | Swagger, code, architecture diagrams |
| USSD self-screening on the simulator, and its SMS | The admin side of the dashboard |
| The hospital worklist and the population view | Anything not yet built |

## 6.2 Shot-by-shot plan — five minutes

| Time | Segment | What is on screen | Voiceover carries |
| --- | --- | --- | --- |
| 0:00–0:30 | The problem | Three numbers on plain cards: 500,000 miners · 19% silicosis · 141 years at current pace | Why this exists, in three sentences. No music over the voice. |
| 0:30–1:00 | What it is | The one-sentence description, then the architecture as a simple left-to-right flow | One breath: who uses it and what it does. |
| 1:00–2:15 | Screening a returning miner | Real device in hand. VHW opens the app, looks up a miner by phone number, answers a few questions, submits. | This is a miner screened three months ago. Watch what the system remembers. |
| 2:15–2:50 | The result | Four-level result card: level, Shona and English explanation, the personalised advice line, and the 'changed since last screening' note | The deterioration line is the moment. Let it sit for two seconds. |
| 2:50–3:25 | The referral, and a real SMS | Referral card with facility, deadline and code — then cut to a physical phone as the SMS lands | This referral is now a tracked object with a deadline, not an instruction. |
| 3:25–4:10 | USSD self-screening | The feature-phone simulator. Dial the code, answer questions, then the result SMS arrives on the handset. | Say plainly it is our simulator pending the shortcode application, and that the SMS is real. |
| 4:10–4:40 | The hospital and population view | Dashboard: today's referral worklist, then tier distribution and the weekly narrative | Same data, three audiences: the hospital, the district, the country. |
| 4:40–5:00 | Close | One card: what is live, what is not, and the ask | End on the ask. Do not trail off. |

## 6.3 Production notes

- One voice, scripted — Write the voiceover as a script and read it. Do not improvise over footage — five minutes is too tight to waste on filler words.

- Burn in captions — Reviewers may watch without sound while testing files. Captions also carry the Shona strings for a non-Shona-speaking judge.

- Real device footage matters — A phone in a hand is more persuasive than a screen recording. Use screen recording for the dashboard, real footage for the app and the arriving SMS.

- Seed clean demo data first — The numbers on screen must be plausible and consistent between shots. Re-seed before shooting, not during.

- Shoot more than you need — Multiple takes of the screening and the SMS arrival. The SMS timing is the shot most likely to need retries.

- Export conservatively — 1080p MP4, H.264, under the organisers' size limit if one is given. Test playback on a machine that is not yours before submitting.

CRITICAL: Feature freeze must be 20 August so the system is stable for the shoot on 21 August. Filming against a system that is still changing wastes the day and produces inconsistent footage.

## 6.4 The live prototype requirement

Judges may ask for a live demonstration on the day. That means the deployed backend, the seeded demo data, the USSD simulator and the dashboard must all still be working on 28 August — four days after submission and eight days after freeze. Two specific risks:

- The database must not be asleep. See Section 16.2 — a free Supabase project pauses after seven days of inactivity.

- The demo phone must be charged, registered with the SMS provider, and tested the morning of the showcase, not the week before.

# Section 7 | Implementation & Pilot Strategy

## 7.1 Proposed pilot site and users

| Element | Specification |
| --- | --- |
| Location | Kwekwe District, Midlands Province — highest documented burden, established artisanal mining community, and a named receiving hospital |
| Sites | 3–5 high-density artisanal mining hubs within the district |
| Delivery staff | 10 village health workers, trained over one day, working roughly two field days a week |
| Miners | Target 5,000–9,000 screened over six months (see 7.4) |
| Receiving facility | Kwekwe District Hospital — outpatient and respiratory departments |
| Duration | Six months in three phases |

## 7.2 The three phases

| Phase | Window | What happens |
| --- | --- | --- |
| Micro-site selection and baseline | Months 1–2 | Select the sites. Map VHW coverage. Establish the referral pathway with the hospital. Secure syndicate and traditional leadership permission. Record baseline late-stage presentation rates so we can measure change. |
| Active and passive rollout | Months 3–5 | Active: VHW teams run weekly sweep days, each opening with a Teach Mode session. Passive: the USSD code broadcast via community radio, posters at hammer mills, and syndicate word of mouth. Deterioration detection tested across successive screenings. |
| Evaluation and optimisation | Month 6 | Measure KPIs. Validate triage performance against radiological confirmation in a subsample. Refine the AI modules. Package results for MoHCC, NSSA and funder conversations. |

## 7.3 Required partners and resources

| Partner | What they provide | What they get | Status |
| --- | --- | --- | --- |
| Kwekwe District Hospital | Referral destination, clinical oversight, outcome confirmation | Pre-alerted referrals instead of unannounced walk-ins; first population-level view of their catchment | To approach — priority |
| Midlands Provincial Health / MoHCC | Authorisation to operate; integration with district reporting | A digital occupational health register they do not currently have | To approach |
| ASM associations and syndicate leadership | Site access, community trust, peer mobilisation | Health service for their members at no cost | To approach — nothing happens without them |
| Cimas | Distribution, credibility, potential first funder | Respiratory risk intelligence on an insured mining population | Competition host — natural first conversation |
| Mobile network operator | USSD shortcode and SMS delivery | Commercial traffic; visible public health contribution | Application to start immediately |
| MRCZ | Ethical clearance for research on a vulnerable population | Compliant, publishable pilot | Application to prepare |

OPEN / VERIFY: We have not approached any of these organisations yet. Never imply we have. The correct phrasing is: 'these are the conversations we are sequencing, and Cimas is the natural first one given this competition.'

## 7.4 Indicative costs and timeline

| Category | Item | Basis | USD |
| --- | --- | --- | --- |
| Hardware & infra | Android devices for VHWs | 10 × $130 | 1,300 |
| Hardware & infra | Cloud hosting, database and AI backend | 6 mo × $150 | 900 |
| MNO & USSD | Shortcode provisioning and monthly fees | 6 mo × $200 | 1,200 |
| MNO & USSD | SMS — results, reminders, escalations, outreach | 10,000 × $0.03 | 300 |
| Field ops | VHW stipends and transport | 10 × 6 mo × $80 | 4,800 |
| Field ops | Stakeholder workshops — hospital, ZMF, syndicates | 2 × $400 | 800 |
| Field ops | Mobilisation, translated materials, N95 demonstration stock | bulk | 400 |
| Governance | MRCZ ethical clearance and filing | lump sum | 500 |
| Governance | Coordination, supervision and evaluation report | 6 mo × $500 | 3,000 |
| TOTAL | Six-month pilot, all in |  | 13,200 |

Modelled reach at conservative assumptions — ten VHWs, eight field days a month each, twenty screenings a day — is about 1,600 screenings a month, or roughly 9,600 over six months. That puts the cost in the region of $1.40 per miner screened. Present the model and its assumptions rather than the single number, and offer the sensitivity: at half that throughput it is still under $3 per screening.

OPEN / VERIFY: Every figure is an informed estimate, not a quote. Before presenting externally: get a real rate card for USSD and bulk SMS, confirm current MRCZ fees and turnaround, and sanity-check the VHW stipend against NGO field-worker rates in Midlands Province.

## 7.5 Success measures

| Metric | Definition | Why it matters |
| --- | --- | --- |
| Referral completion rate | ORANGE and RED referrals confirmed attended within the urgency window | The headline. Falsifiable, and directly comparable to the documented 73% baseline. This is what funders will judge us on. |
| Screening reach | Total miners screened, split by app and USSD | Proves the delivery model works and quantifies the self-service channel |
| Time to referral attendance | Median days from screening to confirmed attendance | Proves speed improvement over the status quo |
| Re-screen attendance | Proportion attending their scheduled re-screen | Proves surveillance, not just screening, is viable |
| Deterioration detected | Miners flagged deteriorating on re-screen | Would be the first such dataset in Zimbabwe for this population |
| Triage performance | Observed sensitivity and specificity against radiological confirmation in a subsample | The honest answer to 'how accurate is it' — and a publishable output |

# Section 8 | The Ask

The template asks what we need to move from here into a real-world pilot. Be specific and be short. Vagueness here reads as not having thought about it.

## 8.1 The primary ask

Say this

“We need three things to run the Kwekwe pilot. Thirteen thousand two hundred dollars for six months. An introduction to MoHCC's Directorate of Epidemiology and Disease Control, which Cimas already sits close to. And a mobile operator willing to expedite a USSD shortcode. The software is built and tested. What we need is permission, a phone number, and six months of field costs.”

## 8.2 The full list, in priority order

| What we need | From whom | Why it unblocks us |
| --- | --- | --- |
| Pilot funding — US$13,200 for six months | Cimas as first mover; or a co-funding structure | Covers devices, VHW stipends, connectivity, ethics and evaluation. This is the whole gap between a working system and a running programme. |
| Introduction to MoHCC Directorate of Epidemiology & Disease Control | Cimas, or the mentor network | Authorisation to operate in-district and integration with national reporting. Without this we are a private app; with it we are national surveillance infrastructure. |
| A named receiving facility agreement | Kwekwe District Hospital, via provincial health | Referrals need a destination that has agreed to receive them. This is the difference between a referral and a suggestion. |
| Expedited USSD shortcode | Econet or NetOne, ideally via a Cimas commercial relationship | The self-screening channel is our reach differentiator and it is the one thing we cannot build ourselves. |
| Clinical governance | A registered occupational health physician | Sign-off on patient-facing content and supervision of the pilot. Gabriel leads clinically but is a student; the pilot needs a supervising clinician. |
| MRCZ ethical clearance support | Institutional sponsor | Required to collect health data from a vulnerable population and to publish the results. |

## 8.3 What we are not asking for

Worth saying explicitly, because it signals we know what we already have: we are not asking for engineering funding, and we are not asking anyone to build anything. The backend, the four AI modules, the mobile app, the USSD layer and the dashboard exist and are tested. The ask is entirely about access, permission and field costs.

PART B

Strategic depth — for questions, not for slides

# Section 9 | The National Policy Opportunity

Can SilicaGuard be Zimbabwe's first step toward implementing the basic occupational health services model? Yes — and this is the strongest strategic frame available to us. Worth one slide and worth having ready as an answer.

## 9.1 The policy gap is already officially named

Basic Occupational Health Services (BOHS) is not our idea. It is a formal model developed jointly by the WHO, the ILO and the International Commission on Occupational Health in 2003, with a published guideline in 2005. It applies primary health care principles to workers' health, and exists precisely because occupational health services are unavailable to more than 80% of the world's workforce — overwhelmingly informal workers, the self-employed and people in small enterprises. Southern Africa is explicitly named in the literature as a region where BOHS is urgently needed.

Zimbabwe's position is documented by its own occupational health researchers: the country has not implemented the model that integrates occupational health services into primary healthcare. Their published recommendation is that national policy should do exactly that, starting in districts with high artisanal mining activity.

The frame

Zimbabwe's occupational health gap is not a knowledge gap. The model is internationally defined, the recommendation is published by the country's own specialists, and the target districts are already named. It is a delivery gap. SilicaGuard is delivery infrastructure for a policy that already exists on paper.

## 9.2 What BOHS requires, and how much of it we already are

| BOHS requirement | SilicaGuard status |
| --- | --- |
| A register of workers and their exposure history | BUILT. Worker register keyed to phone number, cumulative exposure captured every screening. |
| A structured screening instrument applied systematically | BUILT. Ten bilingual questions, identical across app and USSD. |
| Risk stratification and prioritisation | BUILT. Four levels with hard clinical safety overrides the AI cannot bypass. |
| Periodic health surveillance on a schedule | BUILT. Deterioration detection on every re-screen; re-screen intervals defined per level. |
| A referral pathway to definitive diagnosis | BUILT. Facility matching, deadlines, pre-alert, reminder cascade, escalation, attendance confirmation. |
| Record keeping and reporting to public health | BUILT. Full audit trail; live population intelligence for MoHCC and district health. |
| Clinical examination, radiography, spirometry, laboratory | NOT OURS, AND SHOULD NEVER BE. Stays with the clinic and hospital. We route to it and prioritise the queue. |
| Workplace hygiene assessment and dust measurement | NOT BUILT. A genuine gap. Name it as a future module rather than pretend otherwise. |

Six of the eight components are information problems, and we have built all six. The two we have not are the two requiring a clinician or an industrial hygienist physically present — exactly the two that should stay with MoHCC.

# Section 10 | Learning From What Came Before

## 10.1 Who does what in the incumbent model

| Organisation | Role | What it means for us |
| --- | --- | --- |
| USAID | Funder, via the TB Local Organization Network mechanism | Precedent that this exact work is fundable. Also the cautionary tale. |
| Union Zimbabwe Trust | Prime recipient and consortium lead | The kind of organisation that would host us — holds grants, needs delivery infrastructure |
| Baines Occupational Health Services | Runs the actual miner screening — clinics and mobile | Not a competitor. See 10.2. |
| Jointed Hands Welfare Organization | Community mobilisation and demand creation | The function we need and cannot build ourselves. Natural implementation partner. |
| MoHCC | Staff, consumables, laboratory; owns follow-up of all screened miners | Data partner and eventual public-sector customer. We make their follow-up obligation deliverable. |
| Provincial medical office | Coordinates each screening event | Operational gatekeeper for district rollout |
| ASM associations and syndicates | Youths in Mining, Women in Mining, cooperatives; miners recruited as logistic officers | The access mechanism. No outreach happens without them. |

OPEN / VERIFY: Acronym collision: in the literature BOHS means both Baines Occupational Health Services and Basic Occupational Health Services. Be explicit about which you mean or you will confuse a knowledgeable judge.

## 10.2 Is Baines a competitor?

They are not, because we are not in the same business. Baines does clinical occupational health — radiographs, spirometry, audiometry, physical examination, diagnosis — with occupational health physicians and nurse practitioners. We do none of that. SilicaGuard is triage, tracking and data. Their output is a diagnosis; ours is a prioritised, tracked queue.

They are in fact the ideal customer and the ideal delivery partner. Their published lessons learned describe our feature list as their unsolved problems: 73% preventive therapy initiation because follow-up fails, screening blocked by X-ray downtime, data on paper and manually imported to Excel. If a specialist provider wins the next grant, they will need exactly what we built. We are infrastructure they run their programme on, not a rival bidding against them.

The real risk, stated plainly: not that they out-compete us for miners, but that they or any implementer builds a simple version internally rather than adopting ours. Our defence is being first, being genuinely good, being embedded with Cimas, and being cheap enough that building it is obviously worse value. Say this openly if asked — a team that can name its own competitive risk reads as serious.

## 10.3 What funders in this space require

| Requirement | Our position |
| --- | --- |
| Measurable case finding per dollar | Referral completion rate is our headline KPI and it is falsifiable |
| A local implementing partner, not a foreign vendor | Zimbabwean team, Harare-based, piloting in Kwekwe |
| Alignment with national policy and MoHCC reporting | Section 9 — delivery layer for a published national recommendation |
| Ethical clearance and data governance | MRCZ application planned; phone numbers hashed at rest; consent captured at screening |
| Evidence of reaching the hard-to-reach | USSD self-screening reaches miners no outreach day catches |
| Sustainability beyond the grant | Three independent payer paths, none of them the miner |
| Cost per outcome beating the alternative | Our marginal cost per additional screening is roughly one SMS |

# Section 11 | What SilicaGuard Adds

| What exists and works | What is missing | What we add |
| --- | --- | --- |
| Trusted institutional presence and community access | Nothing operating between events | A layer that runs 365 days a year |
| Excellent one-time clinical assessment with real diagnostics | No memory of the miner across visits | Longitudinal record; deterioration detection on every re-screen |
| A referral instruction, given verbally | No tracking; 73% follow-through | Referrals tracked with deadlines, reminders, escalation and confirmed attendance |
| Paper registers and retrospective Excel | No live surveillance picture | Live population intelligence for MoHCC, NSSA, Cimas, hospitals and the Ministry of Mines |
| Screening capped by fleet and equipment | Cannot scale past ~3,500 a year | Marginal cost of one more screening ≈ one SMS |
| Outreach reaching miners present on the day | Remote or absent miners missed entirely | USSD self-screening from any phone, any day, same questions, same result |

# Section 12 | Why AI, and Other Hard Questions

## 12.1 Why AI at all

A clinically literate judge may push here, and there is a real counter-argument: in community TB screening, roughly half of bacteriologically positive cases are symptom-screen negative. If raised, concede it immediately — it is true, and it is exactly why we do not claim to be a diagnostic. Then give these five reasons.

- Consistency without a clinician in the room — Zimbabwe has very limited occupational health capacity and two dedicated clinics nationally. AI makes an expert-shaped triage reproducible in a VHW's hands after two days of training.

- Pattern across time — No chest X-ray tells you a miner's cough is new. Comparing this screening to his last is information a one-off assessment cannot generate, and impossible to run at scale on paper.

- Triage economics — Radiology is the bottleneck — proven by their own data on screening dropping out during X-ray downtime. We order the queue so the scarcest resource sees the highest-risk miners first.

- National-scale precedent — WHO's 2021 TB screening guidelines endorsed computer-aided detection for chest radiograph interpretation. AI is already inside the WHO-endorsed TB pathway. We apply the same logic one step upstream, where there is currently nothing.

- Safety is engineered, not prompted — Hard red-flag overrides execute in code after the model returns. Severe breathlessness, severe chest pain, active TB or prior lung diagnosis always force the highest level. The model cannot downgrade it. This sentence ends the 'what if the AI is wrong' question.

## 12.2 Settled answers to everything else

| Question | Answer |
| --- | --- |
| Isn't this already being done? | In two-to-three week bursts, funded by grants cancelled twice in two years. That is the problem. We are the persistent layer in between. |
| Are you replacing doctors? | No. We decide who needs a doctor and make sure they reach one. Every high-level result goes to a clinician. |
| What if the screening misses someone? | It will — no triage is perfect, and about half of TB cases are symptom-negative. That is why every miner has a scheduled re-screen and why deterioration detection exists. We catch on the second pass what we miss on the first. Today there is no second pass at all. |
| Who validates the clinical logic? | Our Clinical Lead signs off every rule and every patient-facing string. Validation against radiological confirmation is the pilot's primary research output. |
| Why would a miner dial a code for a disease he cannot feel? | Mostly he would not, unprompted — which is why USSD is the passive channel behind active outreach, not a standalone strategy. Comparable self-screening campaigns show uptake spikes with promotion and decays within weeks without it. The Outreach Planner exists to keep prompting. |
| What about privacy for informal operations? | Phone numbers hashed at rest, consent at screening, compliance with the Cyber and Data Protection Act, MRCZ clearance for the pilot. We are a public health tool, not an enforcement mechanism, and miners must be told that plainly. |
| Is this a medical device? | No. A public health screening and triage support tool. It stratifies risk and routes to care; it does not diagnose. That keeps us in public health pathways rather than device regulation. |
| What if a judge asks about the 5% of miners with no phone at all? | They are reached the same way they are today — in person, by the health worker, on outreach day. The phone channels are additive reach, not the floor. |

# Section 13 | The Product

## 13.1 The four AI modules

| Module | What it does | Status |
| --- | --- | --- |
| Risk Stratification Engine | Clinical system prompt returning level, confidence, contributing factors, bilingual explanation and a personalised advice line from the miner's weakest answer. Hard red-flag overrides run in code outside the model. | Live |
| Longitudinal Deterioration Detection | Compares every re-screen to the most recent prior screening. Any worsened answer escalates the level, even where today's score alone would not have flagged him. | Live |
| Smart Referral Router | Urgency window, facility matching, SMS pre-alert, reminder cascade, escalation on deadline breach. | Live |
| Population Health Intelligence | Plain-language weekly narrative plus level distribution and site breakdown, computed live, with a deterministic fallback if the AI call fails. | Live |

Nothing else is called AI. The mobile UI, USSD tree, SMS dispatch and Outreach Planner are deliberately not described as AI — overclaiming would weaken these four real claims.

## 13.2 Re-screen intervals

| Level | Clinical action | Re-screen interval |
| --- | --- | --- |
| Level 1 (GREEN) | Education and advice line only | 12 months |
| Level 2 (YELLOW) | Watch. Education, advice line, added to watch worklist | 6 months |
| Level 3 (ORANGE) | Referral within 14 days | 3 months after referral outcome |
| Level 4 (RED) | Referral within 48 hours | Per clinical outcome; held open until closed |

OPEN / VERIFY: Drafted for structure, not clinically validated. Gabriel must confirm or correct each interval against occupational health surveillance practice before it is presented or coded as final.

## 13.3 Levels, not colours, at the SMS boundary

Internally the database keeps the colour. At the SMS and USSD boundary it maps to a numbered level with an action phrase in Shona and English, because colour does not survive plain text.

| Level | Example message stem |
| --- | --- |
| Level 1 | Level 1 — Wakanaka. Ramba uchishandisa mask yako. (You are well. Keep using your mask.) |
| Level 2 | Level 2 — Ngwarira. Dzokera kunotariswa mumwedzi mitanhatu. (Take care. Come back for a check in six months.) |
| Level 3 | Level 3 — Enda kuchipatara mumazuva gumi nemana. (Go to the clinic within fourteen days.) |
| Level 4 | Level 4 — Enda kuchipatara nhasi. (Go to the hospital today.) |

OPEN / VERIFY: All Shona strings are drafts written for structure. Every one needs Clinical Lead sign-off and native-speaker review before it reaches a real miner — or appears in the video.

# Section 14 | Who Pays

Rewritten from v4.0, which made formal mining employers the primary revenue stream — directly contradicting the artisanal-only scope. They are removed entirely.

## 14.1 Who never pays

| Stakeholder | What they get | Pay? |
| --- | --- | --- |
| Artisanal miners | Free screening; USSD self-screen any time; group education plus personalised advice; SMS results and reminders; a referral tracked until it closes | Never. Any model requiring them to pay is commercially futile and ethically wrong. |
| Village health workers and nurses | Practitioner app: offline screening, Teach Mode, referral generation, follow-up worklist, outreach planner | No. They are the delivery mechanism. |
| District hospitals | Dashboard, referral queue, pre-alerts, code lookup | Free during pilot; small public-sector licence later. |

## 14.2 Three independent payers, none of them the patient

| Payer | Model | Why they pay |
| --- | --- | --- |
| Insurers — Cimas first | Subscription per covered member, or programme sponsorship | Early detection is dramatically cheaper than late-stage respiratory admission. Cimas is our natural first conversation and gains respiratory risk intelligence on a population nobody currently sees. |
| Public sector — MoHCC and NSSA | Annual platform licence, or surveillance commissioning | Provides the national occupational health register the country does not have, and delivers the BOHS integration MoHCC's own researchers recommended. NSSA carries the occupational disease mandate with no structured evidence trail for informal claims. |
| Programme implementers | Per-programme implementation and support fee | They win grants to screen miners and must then build delivery and reporting infrastructure themselves. Renting ours is cheaper, and it comes with the reporting their funder demands. |

The sustainability line

Miners never pay. Insurers pay because early detection is cheaper than late-stage admission. The public sector pays because we provide the register the country has recommended and never built. Programme implementers pay because renting delivery infrastructure beats building it. Three independent payers, and not one of them is the patient.

# Section 15 | The Throughput Model

How many miners can a small team actually screen, and what happens when more arrive than expected? We answer with a model rather than an assertion. Treat a screening station as a queue: miners arrive at some rate, a number of health workers serve them, each screening takes about ten minutes.

L = λW   (Little's Law)        ρ = λ / (c · μ)        throughput ≈ min(λ, c · μ)

Where λ is arrival rate, c is health workers screening, μ is service rate per worker (6 per hour at 10 minutes each), ρ is utilisation, L is number waiting, W is average wait. Built in SimPy in under 100 lines, exporting one chart for the deck.

## Conservative planning numbers

| Variable | Value | Basis |
| --- | --- | --- |
| VHWs deployed | 10 | Pilot budget line |
| Field days per VHW per month | 8 | Two days a week, leaving existing duties intact |
| Screenings per field day | 20 | Six productive hours ÷ 10 minutes, discounted ~45% for travel, queueing, education blocks and refusals |
| Monthly throughput | 1,600 | 10 × 8 × 20 |
| Annualised | 19,200 | ≈ 5.4× the incumbent's 3,556 per year |

OPEN / VERIFY: Never present as achieved. It is a model with stated assumptions. Offer the sensitivity unprompted: even at half these numbers it is roughly 2.7× the incumbent rate. And state the honest limit — their screenings included radiography, sputum, HIV testing and spirometry; ours is symptom-and-exposure triage. Not the same unit of output.

PART C

Execution — ten days

# Section 16 | Product Roadmap to 20 August

Feature freeze is 20 August so the system is stable for the video shoot on the 21st. Ordered by value per engineering hour.

## 16.1 USSD self-screening, and how to demonstrate it

Obtaining a live shortcode requires application to Econet or NetOne and, for some code classes, POTRAZ approval — a commercial and regulatory process on their timeline. Ten days is not enough.

### Simulate the network, not the system

Build a feature-phone simulator as a small web page — a keypad and a green screen rendered in the browser. When the presenter dials the code, it sends exactly the payload a real USSD gateway sends: session ID, service code, phone number and the accumulated text string. Our backend cannot tell the difference, because there is none. Same endpoint, same session logic, same scoring, same record in the same database.

- It is the real code path. We are mocking the telephone network, which is the only part we do not yet have a contract for — not the screening.

- The SMS leg is genuinely real. The result goes out through the actual provider and lands on a physical phone. On video, that is a shot of a real message arriving.

- It removes all live-network risk from the highest-value moment of the demonstration.

How to say it in the video and on stage

“The keypad you are watching is our simulator, because our shortcode application with the network operator is in progress. Everything behind it is production code, and the message arriving on this phone is a real SMS.” Said plainly, that is more convincing than a live network, because it shows we know exactly what is and is not finished.

OPEN / VERIFY: Register the demo phone as a sandbox simulator number with the SMS provider and test end-to-end delivery before 20 August. Confirm SMS coverage for Zimbabwe specifically — v4.0 noted the provider's Voice product does not list Zimbabwe, so do not assume SMS works without testing it.

## 16.2 Postgres migration via Supabase

Supabase is the right call. Verified free tier as of mid-2026: 500 MB Postgres, 1 GB file storage, 5 GB egress, 50,000 monthly active users, two active projects, no backups and no SLA. All comfortably adequate for a pilot except one thing.

CRITICAL: A free Supabase project with no database activity for seven days is automatically paused and takes around thirty seconds to wake. Submission is 24 August and the showcase is 28 August — if nobody touches it in between, it will be asleep when the judges ask for a live demonstration. Do both mitigations: a scheduled keep-alive writing a trivial row every three days, and upgrade to Pro at $25 for the month, which removes pausing entirely.

- Add Alembic for migrations against the existing SQLAlchemy models.

- Watch the usual SQLite-to-Postgres breakages: timezone-aware datetimes, strict boolean typing, implicit type coercion SQLite has been tolerating.

- Run the full test suite against Postgres before touching anything else. A green suite on the new database is the definition of done.

## 16.3 React dashboard

- Stack — Vite + React + TypeScript, TanStack Query, Recharts, Tailwind with shadcn/ui, and a mapping library for the site map.

- Four role views over one dataset — MoHCC — district surveillance and weekly narrative. NSSA — occupational disease burden. Cimas — cost, volume, referral completion. Hospital — today's referrals with tap-to-call. Same data, different lens.

- What makes it look expensive on video — Real numbers everywhere, no placeholder text. A live referral queue. Level distribution over time rather than a static pie. A map with density. Consistent spacing and one accent colour beats any animation.

## 16.4 Offline capability

Non-negotiable for field credibility — a screening tool that fails without signal is not a field tool. Minimum viable version: the app holds the question bank locally, writes screenings to local storage, applies the deterministic scoring rules offline to produce a provisional level, and queues for sync. On reconnection, records upload, the AI explanation and advice line generate server-side, and referrals and SMS fire.

The honest framing, and worth one line in the video: the safety-critical part — the level — is computed offline by deterministic rules, so a miner is never left without an answer. The AI explanation arrives when the phone reconnects. This demonstrates the safety logic does not depend on the network or the model.

## 16.5 Teach Mode

Six illustrated full-screen cards with a script underneath. The health worker holds the phone up and talks a group through them — fifteen minutes, live, in Shona, with questions allowed. The point is not the technology; it is that a VHW with two days of training delivers the same session a nurse would, every time.

| Card | Title | What the health worker says |
| --- | --- | --- |
| 1 | What the dust does | Silica dust is too small to see. It goes deep into the lungs and stays there forever. The lungs slowly harden and stop working. |
| 2 | Why it is silent | You can feel completely fine for ten years while the damage is happening. By the time you cannot breathe, it is too late to reverse. |
| 3 | The mask that works | A cloth mask does nothing against silica. Only an N95 or FFP2 respirator works. Here is how to fit it so it seals. |
| 4 | Water changes everything | Drilling dry throws silica into the air. Drilling with water suppresses it. This single change is the biggest protection available. |
| 5 | The signs that mean go now | Cough lasting over three weeks. Breathless doing things that used to be easy. Chest pain. Losing weight without trying. |
| 6 | What help exists | If a doctor confirms silicosis, here is where to go and what to bring. |

OPEN / VERIFY: Card 6 was originally about NSSA compensation. Compensation generally requires formal employment, which most artisanal miners do not have. Gabriel must rewrite it to describe what is actually available to an informal miner — promising a pathway that does not exist would be worse than saying nothing.

## 16.6 Referral code

Short human-readable code per referral, sent by SMS to the miner and included in the facility pre-alert. One hospital-side web page where staff enter the code, see the record and confirm attendance — which closes the referral automatically. This is what makes referral completion measurable, so it is worth building before anything cosmetic.

# Section 17 | Brand

## Vision

A Zimbabwe where no miner loses his lungs to the work that feeds the nation — where every worker exposed to occupational lung hazards is on a register, is educated in his own language, is re-screened on schedule, and is referred and followed up when his risk changes.

## Mission

To give every artisanal miner in Zimbabwe a lung health record that follows him — screening him where he works, catching deterioration before it disables him, telling him the one thing that would most change his outcome, and making sure a referral ends at a hospital rather than in a notebook.

## Motto

Screen. Track. Follow Through.

## Logo

- Concept — A lung silhouette whose lower lobes resolve into a shield, or a bronchial branch rendered as a signal motif — connecting 'lung' and 'digital layer' in one mark.

- Constraint — Must survive being one centimetre high on a printed handout and rendered as a monochrome app icon. No gradients, no fine detail.

- Palette — Navy #1E2761 and mint #02C39A. A third accent only if it earns its place.

- Route and deadline — Commission it today. It must exist by 19 August so it can appear in the video, on the deck and on the handout. Do not spend team-days on it.

# Section 18 | Deliverables

| Deliverable | Due | Owner | Notes |
| --- | --- | --- | --- |
| 5-minute prototype video | 24 Aug (shoot 21, edit 22–23) | Takudzwa + Panashe | The primary demonstration. Section 6 is the plan. |
| Final presentation deck | 24 Aug | Panashe | Built directly from Part A, in the organisers' section order |
| Printed handout for adjudicators | 27 Aug | Takudzwa | One double-sided A4, point form, mirroring the deck so judges can follow |
| Digital banner | 27 Aug | Takudzwa | Vertical flow: name, three numbers, four pillars, architecture, QR to the demo |
| Live prototype, stable | 28 Aug | Panashe | Deployed, seeded, database awake, demo phone charged and tested |
| Validation log | 21 Aug | Gabriel | The stakeholder engagement table from Section 4.2 — this becomes a slide |
| Backup demo video | 23 Aug | Panashe | Separate from the submitted 5-minute film; insurance for the live demo |

## 18.1 Handout anatomy

| Section | Content |
| --- | --- |
| Header | Logo, one-sentence description, team names and roles, contact |
| The problem | Four numbers: 500,000 miners · 19% silicosis · 39× TB rate · 141 years at current pace |
| What SilicaGuard is | Three sentences maximum |
| Capabilities | Icon grid with LIVE / IN PROGRESS flags |
| How we complement MoHCC | The two-column 'what exists + what we add' framing |
| The BOHS opportunity | One paragraph from Section 9 |
| Pilot | Kwekwe, 6 months, 3 phases, US$13,200, three KPIs |
| The ask | The three-part ask from Section 8.1 |
| Evidence | The citation list from Appendix A — this page makes us look like researchers |
| Honest gaps | What is not built. Judges notice, and it helps us. |

# Section 19 | Division of Labour

| Person | Owns | By 20 August | 21–24 August |
| --- | --- | --- | --- |
| Panashe | Backend, USSD and SMS, Supabase, referral code, models, architecture narrative | USSD simulator with real SMS delivery; Supabase live with green tests; referral code flow; throughput model charted | Video technical footage; deck built from Part A; submission |
| Takudzwa | Dashboard, mobile app, offline, all visual output | Four-view dashboard deployed; offline screening working; Teach Mode cards; logo delivered | Video shoot and edit; handout and banner design |
| Gabriel | Clinical validity, patient-facing copy, stakeholder engagement, pilot research design | Stakeholder interviews logged; every Shona string signed off; re-screen intervals confirmed; Card 6 rewritten | Validation slide; clinical Q&A prep; video voiceover review |
| Shared | Rehearsal and contingency | — | Three timed rehearsals 25–27 Aug; printed materials collected; logistics |

# Section 20 | Timeline

| Date | Focus |
| --- | --- |
| Fri 14 Aug | Lock this document. Commission logo. Start the USSD shortcode application. Begin Supabase migration. Gabriel starts booking stakeholder conversations. |
| Sat 15 – Sun 16 Aug | Supabase migration complete, all tests green. USSD simulator built and hitting the real endpoint. First stakeholder interviews. |
| Mon 17 – Tue 18 Aug | USSD end-to-end with real SMS delivery. Dashboard build. Referral code flow. Interviews continue. Clinical copy review. |
| Wed 19 Aug | Offline capability. Dashboard polish with maps and charts. Teach Mode cards. Logo delivered. |
| Thu 20 Aug | FEATURE FREEZE. Everything working. Re-seed clean demo data. Nothing changes after today. |
| Fri 21 Aug | VIDEO SHOOT DAY. All footage captured, multiple takes. Validation log finalised. |
| Sat 22 Aug | Video edit. Deck built from Part A. First internal review. |
| Sun 23 Aug | Video final cut with captions. Deck final. Backup demo video recorded. Full internal review. |
| Mon 24 Aug | SUBMIT. Early in the day, not at the deadline. Test the video plays on a machine that is not ours. |
| Tue 25 – Wed 26 Aug | Rehearsal. Three full timed run-throughs. Q&A drilling against Section 12. |
| Thu 27 Aug | Printed materials collected. Logistics, travel, device charging. Confirm the database is awake and the demo phone works. |
| Fri 28 Aug | FINAL SHOWCASE. |

CRITICAL: The 24th is the real deadline. Everything before it is build; everything after it is rehearsal. Do not let the 28th feel like the deadline — by then the work is already submitted and only the delivery is left.

# Section 21 | Open Questions

| Question | Best current answer | Action / owner |
| --- | --- | --- |
| Venue, order and judging arrangements | To be communicated separately by the organisers. | Watch for it; adjust logistics when it lands |
| Video file format and size limit | Not specified in the email. | Ask the organisers directly this week — do not guess and re-export at the deadline |
| Is there a slide count or time limit for the live presentation? | Not specified beyond the video's 5 minutes. | Ask. Build the deck to roughly 10 minutes and cut if told otherwise |
| SMS provider coverage for Zimbabwe | Working in sandbox. Voice product does not list Zimbabwe, which raises a question about depth of coverage. | Test delivery to a real Zimbabwean number this week — Panashe |
| MRCZ fee and turnaround | Budgeted $500 as an estimate. Unconfirmed. | Contact MRCZ — Gabriel |
| KNTB total funding value | Cooperative agreement number is public (72061319CA00003); the value is not in the report. A cost-per-screening comparison would be very favourable to us. | Search USAID public award databases — Panashe |
| Does Cimas have an existing occupational health product? | Unknown. If so, the pilot could attach to it commercially rather than starting cold. | Ask Dr Bopoto directly — fair question to a mentor |
| Documentary source for the Kwekwe mortality figure | Currently traceable to a newsletter citing Dr Gunda, verified by phone. | Obtain something written, or present it exactly as attributed — Gabriel |
| Is 'SilicaGuard' trademarked by anyone? | Unchecked. | Search before printing materials |

# Appendix A | Evidence Base

Every number used on stage or in the video must trace to this table. Anything not here does not get said.

## Health burden

| Claim | Figure | Source |
| --- | --- | --- |
| Silicosis prevalence, community study | 19% (n = 3,821); TB 6.8%; HIV 18%; mean age 35.5 | Moyo et al., IJERPH 2022, 19:13822. DOI 10.3390/ijerph192113822 |
| Silicosis, screened cohort | 21% (2,150 of 10,282) | Moyo et al., IJERPH 2024, 21:70. DOI 10.3390/ijerph21010070 |
| TB prevalence in miners | 7.4% (793 of 10,668) | IJERPH 2024, 21:70 |
| HIV at occupational health clinics | 30% (578 of 1,904 with recorded results) | IJERPH 2024, 21:70 |
| TB burden versus general population | 7,400 per 100,000 versus 190 per 100,000 — 39× | IJERPH 2024, 21:70 |
| Compounding risk | Silicosis 3–4×; HIV 5–6×; both >15× | IJERPH 2024, 21:70 |
| Preventive therapy initiation | 73% (1,212 of 1,665 eligible) | IJERPH 2024, 21:70 |
| Population size | Over 500,000 miners; ~2 million dependants | PACT 2015, cited in IJERPH 2024 |
| KNTB totals | 10,668 screened; 3,453 at clinics; 7,215 mobile; Oct 2020 – Sep 2023 | IJERPH 2024, 21:70 |
| Health workers trained | 370 (84 doctors, 167 nurses, 102 EHTs, 17 miners) | IJERPH 2024, 21:70 |

## Economic weight

| Claim | Figure | Source |
| --- | --- | --- |
| Mining share of economy | ~14% GDP, 75% export earnings, 20% government revenue (2024) | World Bank, via BU Global Development Policy Center |
| Gold share | ~8% national GDP; 54% mining exports; 44% national exports (2025) | Chamber of Mines CEO, June 2026 |
| Artisanal share of gold output | 34.9 of 46.7 tonnes in 2025; large-scale 11.8 tonnes | 2025 full-year Fidelity Gold Refinery figures |
| Formal versus artisanal workforce | ~18,000 formal versus ~500,000 artisanal | Chamber of Mines, June 2026 |
| Dependants | ~2 million directly; ~6 million with a stake | Chamber of Mines, June 2026 |
| H1 2025 mining exports | US$2.81 billion, up 38.6%; gold US$1.38 billion | RBZ Midterm Monetary Policy Statement 2025 |

## Policy and funding

| Claim | Detail | Source |
| --- | --- | --- |
| BOHS model | Developed by WHO, ILO and ICOH in 2003; guideline 2005; occupational health services unavailable to >80% of the global workforce; Southern Africa named as urgently needing it | WHO/ILO/ICOH BOHS guideline and peer-reviewed BOHS literature |
| Zimbabwe has not implemented BOHS | Stated directly in the KNTB report, with a recommendation to integrate occupational health into primary care in artisanal mining districts | IJERPH 2024, 21:70 |
| ZHI grant terminated | US$53,195,423 USAID grant, scheduled to September 2026, terminated in the 2025 funding freeze | Peer-reviewed analysis, PMC12130410 |
| Zimbabwe–US MoU talks halted | February 2026, negotiations formally terminated citing lack of equitable partnership | AVAC Global Health Watch, Feb 2026 |
| WHO endorses AI in TB screening | 2021 guidelines endorsed computer-aided detection for chest radiograph interpretation in those aged 15+ | WHO consolidated guidelines on tuberculosis, 2021 |

# Appendix B | Modelling Research Backlog

The throughput model in Section 15 is the one we build and present. These are researched during the 25–27 August window and deployed later. Each is genuinely applicable; the question is only whether we can parameterise it honestly.

## Model 1 — Site selection as a covering problem

Choosing which mine sites to visit is the Maximal Covering Location Problem. Given candidate sites with estimated miner populations and a travel radius, choose the k sites maximising miners covered.

maximise Σ (a_i · y_i)   s.t.   Σ x_j ≤ k ,   y_i ≤ Σ_{j∈N_i} x_j ,   x, y ∈ {0,1}

Solve with PuLP or OR-Tools; plot the chosen sites. Answers 'how did you choose your pilot sites?' with an optimisation rather than intuition, and improves measurably on the incumbent's method of picking no more than four sites on anticipated reach. Highest value of the four — build this one if any.

## Model 2 — Markov progression model for silicosis

Healthy → Sub-radiological → Simple (ILO 1) → Advanced (ILO 2/3) → PMF → Death

Annual transition probabilities conditioned on continued exposure versus removal. Run screened and unscreened cohorts over ten years. Output is healthy life-years preserved per 1,000 miners screened, which converts to DALYs averted and cost per DALY averted — the language NSSA, MoHCC and any donor economist speaks. Gabriel's model.

OPEN / VERIFY: Transition probabilities must come from published silicosis progression literature. The Ehrlich et al. meta-analysis and the South African gold miner cohort studies cited in the KNTB paper are the starting points. If they cannot be sourced honestly, present the structure and state that parameterisation is the pilot's first research output.

## Model 3 — Care cascade

Reaching care = p_screen × p_flag × p_refer × p_attend × p_treat

The incumbent gives one hard anchor: 73% preventive therapy initiation. Our claim is narrow and testable — the referral cascade raises p_attend. Define the baseline from that figure, define the target, make the difference the pilot's primary endpoint. The most fundable claim we have, precisely because it is falsifiable. Low build cost.

## Model 4 — Bayesian triage performance

PPV = (Se·P) / [Se·P + (1−Sp)(1−P)]        NPV = [Sp(1−P)] / [(1−Se)P + Sp(1−P)]

At P = 0.19, a triage with sensitivity 0.80 and specificity 0.70 would give a positive predictive value around 0.39 and a negative predictive value around 0.94. Validation design: radiograph a random subsample of low-level results alongside all high-level results, and compute observed performance against the radiological read.

OPEN / VERIFY: The 0.80 and 0.70 figures are illustrative parameters demonstrating the calculation. They are not measured performance of our tool and must be labelled as such wherever shown.

## Model 5 — Economic return

34.9 tonnes ÷ 500,000 miners ≈ 70 g of gold per miner per year

At 2025 gold prices around US$3,600 per ounce, roughly US$8,000 of output per artisanal miner per year. Against a six-month pilot cost of US$13,200, only a small number of preserved productive careers returns the investment several times over.

OPEN / VERIFY: The most seductive number available and therefore the most dangerous. Not all miners mine gold, not all gold is delivered formally, and per-miner output varies enormously. Present as order-of-magnitude with assumptions visible, never as precise. If challenged, concede immediately and pivot to the DALY model.